## Slide 1
Project progress update: DDR, EyePACS and APTOS
Advisor: Navid Amini, PhD
Department of Computer Science
Early Detection of Diabetic Retinopathy
1

## Slide 2: Progress at a Glance
Where the project stands
2
Done
• Data audit: class counts and merge table
• Pipeline on Kaggle: prepare, train, calibrate, evaluate, plot
• Arms A, B, C trained (3 seeds each)
• Internal and APTOS test evaluation
• 14 imbalance runs (incl. geometric augmentation) and 3 extensions
• Checks: duplicates, image properties, augmentation; group DDR split built and arms retrained (1 seed)
Prepared, not yet run
• Evaluation of the group-split models (new dated declaration; test sets opened again)
To do
• Report AUROC, per-grade results and own-source operating points
• Matched-subset checks for APTOS capture confound
• Five seeds, intervals, ECE, Brier
• Write the thesis chapters
Main findings: the original merge teaches the source; in-domain scores are inflated.

## Slide 3: Data: Three Fundus Datasets
Different sizes, grade mixes and cameras
3
DDR
12,522 gradable images. Random 60/20/20 split (7,454 / 2,552 / 2,516): this copy has no official split or patient IDs.
EyePACS
35,108 images. Split by patient: 24,572 train, 5,266 validation, 5,270 test.
APTOS
3,662 images. External test only: never used for training or model selection.
Early DR (grades 1-2) is 41% of DDR, 22% of EyePACS and 37% of APTOS.

## Slide 4
PROGRESS · MEASURED ON THE REAL DDR + EYEPACS LABELS
The EyePACS merge has a measurable cost
Topping up only the short grades links “which dataset” to “how severe”. Measured from the label files alone — no images, no GPU, no training.
SHARE OF EACH GRADE TAKEN FROM EYEPACS
Grade 0
0.0%
Grade 1
79.0%
Grade 2
0.0%
Grade 3
78.7%
Grade 4
43.7%
0.512 bits
of the severity label is recoverable from the dataset name alone — 24.6% of its information
100%
of merged EyePACS images carry disease, so 38.7% of all disease cases are identifiable purely by recognising the camera
0.167 → 0.000
score of a dataset-name-only predictor: under a random split, versus in a single-clinic test
The shortcut is specific to the earliest decision — any disease versus none (AUC 0.694), and useless for referable disease (0.482).
That is exactly the decision this thesis targets, so the merge must be audited rather than assumed safe.
A classifier also tells DDR from EyePACS images with AUROC 0.996. Design consequence: three arms (A DDR only, B source-balanced, C this merge as a negative control), with every result reported per source.
4
Notes: This is what I have measured so far, and it changed the design of the project. Because the top-up is applied only to the short grades, grades 0 and 2 contain no EyePACS images while grades 1 and 3 are nearly 80 percent EyePACS. A quarter of the severity label is recoverable from the dataset name alone. Every merged EyePACS image carries disease, so a model that learns only to recognise the camera gets 38.7 percent of disease cases right with no false alarms — and only for the earliest decision, which is the one I am targeting. So the merge is not just an imbalance fix; it has a cost, and the thesis now measures it.

## Slide 5: Proposed Methods
Three data arms, one change at a time
Same model, image size and epochs; frozen patient-level splits; test sets opened once.
Data DDR, EyePACS, APTOS
Prepare Crop, pad, 512 px
Merge arms A, B, C
Model EfficientNet-B0
Output Calibrated, 95% CI
Imbalance methods tested
Weighted sampler
Class-balanced loss
Focal loss
Strong augmentation
Augmentation control
The three arms
• A: DDR only (clean baseline)
• B: DDR + EyePACS, source-balanced
• C: version 1 merge (negative control)
• C wins on its own test but not on APTOS = it learned the source
Not a new network: the value is the design, the controls and the evidence.
5

## Slide 6: Training Setup and Curves
EfficientNet-B0, 512 px, 10 epochs, 3 seeds per arm
6
Same recipe for every arm
AdamW, learning rate 3e-4, mixed precision. Best epoch chosen on validation only.
Cost on a Kaggle GPU
About 110 s per epoch (A), 450 s (B), 150 s (C): roughly 6 hours for the nine runs.
Raw outputs are overconfident
Fitted temperature T = 1.6 to 2.4 across the nine runs; calibration is fitted on validation.
Validation sets differ by arm, so these curves show convergence, not which arm is better.

## Slide 7: Key Results So Far
Early DR (grades 1-2) vs No DR, mean of 3 seeds, threshold frozen on validation
7
DDR test set
Held-out EyePACS patients
Sensitivity 0.93 with specificity 0.91, as designed: all arms alike.
Same threshold: specificity 0.39 (A), 0.89 (B), 0.013 (C): C flags 99% of healthy images.
The frozen threshold does not transfer across datasets: compare AUROC, not sensitivity.

## Slide 8: What the Checks Found
Three diagnostic checks, using saved files and train/validation data only
8
Duplicates and split
834 candidate groups; 4% of DDR test had a near-duplicate in train. A group split removed it: validation scores barely changed.
Image properties
Image size alone: DDR 0.58, APTOS 0.96, EyePACS 0.53. APTOS is camera-confounded; EyePACS is clean.
Strong augmentation
BatchNorm mismatch from the noise/blur part. Geometric aug on all classes: 0.977; on minority only: 0.834 (a label cue).
Duplicates are not the problem; the APTOS confound and the threshold are.

## Slide 9: Result 4: Imbalance Methods
Sampler, loss and augmentation, one change at a time (single seed, 14 runs)
9
No method beat baseline
Best 0.9772 (geometric aug, all classes) vs baseline 0.9761: inside seed noise.
Augmentation leaked the label
Geometric aug on all classes: 0.977. On minority classes only: 0.834. Strong aug failed for another reason: next slide.
Limit of the test
The score is early-vs-none PR-AUC; rare grades 1, 3 and 4 are not scored separately.
On this metric, plain cross-entropy is as good as every imbalance method.

## Slide 10: What These Results Do Not Show
Read before quoting any number
10
The frozen threshold does not transfer
On EyePACS specificity is 0.39 (A) and 0.013 (C): sensitivity alone is misleading off-domain.
APTOS is confounded by capture
Image size alone predicts APTOS early DR (AUROC 0.96): its 0.994 is not clean evidence of robustness.
DDR: same-patient leakage remains
No patient IDs. Near-duplicates were small (4%) and removed, but a patient's other eye cannot be.
Not yet reported
Confidence intervals, ECE, Brier and five seeds. Per-grade and specificity analyses are post-hoc.
EyePACS, with a patient-level split and clean properties, is the most trustworthy benchmark.

## Slide 11: Conclusions and Next Steps
What the evidence supports so far
11
The merge as written teaches the source
Arm C flags 99% of healthy EyePACS images as DR, matching the label audit.
Source-balancing helps off-domain
Arm B: EyePACS specificity 0.89, AUROC 0.88; DDR sensitivity unchanged.
EyePACS is the clean benchmark
Properties do not predict its labels (0.50 to 0.59); APTOS is confounded (size 0.96); DDR leakage is small.
Next steps
1. Evaluate the group-split models once (new declaration)
2. Report AUROC, per-grade results and own-source operating points
3. Test capture mitigation: size-matched subsets
4. Five seeds, intervals, ECE and Brier
5. Use geometric augmentation on all classes; keep minority-only as the cue control
6. Re-evaluate once; label post-hoc analyses

## Slide 12: THANK YOU
Questions? We’d love to discuss!