## Slide 1
Project progress update: DDR, EyePACS and APTOS
Advisor: Navid Amini, PhD
Department of Computer Science
Early Detection of Diabetic Retinopathy
1

## Slide 2: Progress at a Glance
Where the project stands
2
Done
• Data audit: class counts and merge table
• Pipeline on Kaggle: prepare, train, calibrate, evaluate, plot
• Arms A, B, C trained (3 seeds each)
• Internal and APTOS test evaluation
• 12 imbalance runs and 3 extensions
• Grad-CAM sanity check
Checks prepared, not yet run
• Duplicate-leakage check (step 12)
• Image-property shortcut check (step 13)
• Diagnose the strong-augmentation failure
To do
• Official or patient-level DDR split; retrain
• Report specificity, grade-1 sensitivity, ECE, intervals
• 5 seeds if time allows
• Re-evaluate APTOS after de-duplication
• Write the thesis chapters
Main finding so far: the original merge teaches the model the source (arm C).

## Slide 3: Data: Three Fundus Datasets
Different sizes, grade mixes and cameras
3
DDR
12,522 gradable images. Random 60/20/20 split (7,454 / 2,552 / 2,516): this copy has no official split or patient IDs.
EyePACS
35,108 images. Split by patient: 24,572 train, 5,266 validation, 5,270 test.
APTOS
3,662 images. External test only: never used for training or model selection.
Early DR (grades 1-2) is 41% of DDR, 22% of EyePACS and 37% of APTOS.

## Slide 4
PROGRESS · MEASURED ON THE REAL DDR + EYEPACS LABELS
The EyePACS merge has a measurable cost
Topping up only the short grades links “which dataset” to “how severe”. Measured from the label files alone — no images, no GPU, no training.
SHARE OF EACH GRADE TAKEN FROM EYEPACS
Grade 0
0.0%
Grade 1
79.0%
Grade 2
0.0%
Grade 3
78.7%
Grade 4
43.7%
0.512 bits
of the severity label is recoverable from the dataset name alone — 24.6% of its information
100%
of merged EyePACS images carry disease, so 38.7% of all disease cases are identifiable purely by recognising the camera
0.167 → 0.000
score of a dataset-name-only predictor: under a random split, versus in a single-clinic test
The shortcut is specific to the earliest decision — any disease versus none (AUC 0.694), and useless for referable disease (0.482).
That is exactly the decision this thesis targets, so the merge must be audited rather than assumed safe.
A classifier also tells DDR from EyePACS images with AUROC 0.996. Design consequence: three arms (A DDR only, B source-balanced, C this merge as a negative control), with every result reported per source.
4
Notes: This is what I have measured so far, and it changed the design of the project. Because the top-up is applied only to the short grades, grades 0 and 2 contain no EyePACS images while grades 1 and 3 are nearly 80 percent EyePACS. A quarter of the severity label is recoverable from the dataset name alone. Every merged EyePACS image carries disease, so a model that learns only to recognise the camera gets 38.7 percent of disease cases right with no false alarms — and only for the earliest decision, which is the one I am targeting. So the merge is not just an imbalance fix; it has a cost, and the thesis now measures it.

## Slide 5: Proposed Methods
Three data arms, one change at a time
Same model, image size and epochs; frozen patient-level splits; test sets opened once.
Data DDR, EyePACS, APTOS
Prepare Crop, pad, 512 px
Merge arms A, B, C
Model EfficientNet-B0
Output Calibrated, 95% CI
Imbalance methods tested
Weighted sampler
Class-balanced loss
Focal loss
Strong augmentation
Augmentation control
The three arms
• A: DDR only (clean baseline)
• B: DDR + EyePACS, source-balanced
• C: version 1 merge (negative control)
• C wins on its own test but not on APTOS = it learned the source
Not a new network: the value is the design, the controls and the evidence.
5

## Slide 6: Training Setup and Curves
EfficientNet-B0, 512 px, 10 epochs, 3 seeds per arm
6
Same recipe for every arm
AdamW, learning rate 3e-4, mixed precision. Best epoch chosen on validation only.
Cost on a Kaggle GPU
About 110 s per epoch (A), 450 s (B), 150 s (C): roughly 6 hours for the nine runs.
Raw outputs are overconfident
Fitted temperature T = 1.6 to 2.4 across the nine runs; calibration is fitted on validation.
Validation sets differ by arm, so these curves show convergence, not which arm is better.

## Slide 7: Key Results So Far
Early DR (grades 1-2) vs No DR, mean of 3 seeds, threshold frozen on validation
7
DDR test set
Held-out EyePACS patients
Sensitivity 0.937 / 0.925 / 0.937 (A / B / C): adding EyePACS did not help.
Arm C: sensitivity 0.997 but PR-AUC 0.43 (A: 0.53): it learned the source. B: PR-AUC 0.80.
Preliminary: random DDR split, duplicates unchecked; APTOS (AUROC 0.994) not claimed yet.

## Slide 8: Result 4: Imbalance Methods
Sampler, loss and augmentation, one change at a time (single seed)
8
No method beat baseline
Best (focal gamma 1) 0.9770 vs baseline 0.9761: inside seed noise.
Strong augmentation failed
Both runs reached only about 0.57: training did not work, so this test is inconclusive.
Limit of the test
The score is early-vs-none PR-AUC; rare grades 1, 3 and 4 are not scored separately.
On this metric, plain cross-entropy is as good as every imbalance method.

## Slide 9: Extensions and Sanity Checks
Single-seed runs on DDR, scored on validation
9
Early vs late (stage 2)
Validation AUROC 0.951 at the best epoch: early and late DR separate well on DDR.
Three-class label
Validation PR-AUC 0.974 vs 0.972 for the two-class head (arm A): no meaningful difference.
Colour normalisation
0.973 vs 0.972: no gain, and 3.4 times slower to train (about 380 s per epoch).
Grad-CAM sanity check
Trained vs randomised-weights maps correlate 0.12 and −0.27 in two runs: the maps depend on the model.
Test-set metrics for these runs are not analysed here.

## Slide 10: What These Results Do Not Show
Read before quoting any number
10
DDR split is random
No patient IDs and no official split in this copy: images from one patient can sit in both train and test.
Duplicate candidates
834 candidate groups: 375 cross splits, 39 cross datasets. Under review; DDR and APTOS numbers may be inflated.
APTOS looks too good
Not claimed as robustness until the overlap check is done.
Not yet reported here
Specificity reached, grade-1-only sensitivity, ECE, Brier and 95% intervals (saved in the results files).
The arm C pattern matches the label audit, but it is also unchecked for duplicates.

## Slide 11: Conclusions and Next Steps
What the evidence supports so far
11
The merge as written teaches the source
Arm C is best on its own validation set (0.982) and worst on EyePACS PR-AUC (0.43).
Source-balancing helps EyePACS, not DDR
B lifts EyePACS PR-AUC by 0.27; DDR sensitivity does not improve.
Imbalance methods: no clear gain
All within noise of plain cross-entropy on the primary metric.
Next steps
1. Run the duplicate check and look at the pairs
2. Official or patient-level DDR split; retrain
3. Diagnose strong augmentation; rerun ablations with 3 seeds
4. Report specificity, grade-1 sensitivity, ECE, intervals
5. Re-evaluate APTOS after de-duplication; write up

## Slide 12: THANK YOU
Questions? We’d love to discuss!